## SAFe® SM
| Preguntas | Marca con una X tu respuesta | Respuesta | Aciertos | 39 | Total | 45
1 | According to SAFe, which of the following metrics are reported at the Inspect and Adapt event? |  |  | Calificación | 86.67%
Cumulative value measure
ART cycle velocity
Cumulative value rate
| ART predictability measure | X | X
2 | What is one benefit of PI Planning?
| Allows for faster decision-making | X | X
It aligns the ART to established DevOps practices
It maximizes team capacity
It fosters cross-team dependencies
3 | What is one element on the Scrum Master/Team Coach responsibility wheel?
Facilitate an Agile Team charter workshop
Facilitate Coach Sync
| Facilitate PI Planning | X | X
Facilitate a Community of Practice
4 | According to SAFe, which of the following key traits of effective Scrum Masters/Team Coaches is crucial for team members to accept coaching?
| Empathy | X | X
Optimism
Agreeableness
Fairness
5 | What is one way to ensure a team is holding successful Iteration Reviews and demos?
The team ensures they complete every Story
The team swarms to prepare for demos
| The team demos working functionality | X | X
The team shares improving metrics
6 | Three members of Team C created a new workflow to speed up the testing process. They spent an entire Iteration designing the process but discovered, just before implementation, that the system could not support the workflow. The rest of the team was excited to hear what was learned from the failed experiment. Which of the following characteristics of a high-performing Agile Team is Team C demonstrating?
| A safe environment for taking risks without fear of embarrassment or criticism | X | X
Enjoying the work and working together
Accountability to each other and the organization for reliably completing quality work
Mutual trust that allows for both healthy conflict and reliance on others
7 | Team A wants to use the IP Iteration to continue their "usual work." What is one benefit the Scrum Master/Team Coach could share with the team about using the IP Iteration as intended?
The team can consider additional retrospective action items
The team can find time to participate in ad hoc groups
| The team can participate in hackathons | X | X
The team can perform needed system maintenance
8 | What is one way a Scrum Master/Team Coach can help improve ART performance?
| Facilitate cross-team collaboration | X | X
Communicate the PI Planning agenda
Prioritize the ART backlog for PI Planning
Run an Agile Team charter workshop
9 | What is one Agile development value?
Healthy interactions over detailed plans
Risk-taking over process development
| Customer collaboration over contract negotiation | X | X
Working teams over busy individuals
10 | What is one way a Scrum Master/Team Coach can support Iteration Execution?
| Facilitate team events | X | X
Assign story points for each User Story
Build value stream maps
Prioritize the team backlog
11 | What is one responsibility of a Scrum Master/Team Coach?
Demoing the system
| Improving flow | X | X
Testing the system
Prioritizing the backlog
12 | Which of the following events aligns teams on a train?
Coach Sync
Iteration Planning
Architect Sync
| PI Planning | X | X
13 | What is one trait of a servant leader?
Deflects information that could change the team's work
| Persuades rather than using authority | X | X
Determines the day-to-day activities for the team
Solves problems on behalf of the team
14 | How can teams use Iteration planning to stay aligned on their work?
| By committing to a set of goals to be delivered | X | X
By sharing Stories that could be pairing opportunities
By reviewing its processes before the next iteration
By agreeing on a meeting timebox
15 | What is one Scrum value that can help Agile Teams create transparency?
Persistence
Communication
| Respect | X | X
Empathy
16 | What is one example of an Agile Team development practice?
Tracking regulations
| Demoing frequently |  | X
| Writing requirements | X
Visualizing effort
17 | What is the intended value of the Backlog Refinement event?
The team reviews and improves processes before the next Iteration
| The team is able to prepare requirements for Iteration Planning |  | X
The team is able to commit to a set of goals to be delivered in the Iteration
| The team aligns on the progress of Iteration Goals | X
18 | What is one Agile practice teams can use to enhance their performance?
Visualize meeting times
| Build in quality | X | X
Use planning cycles
Record innovations
19 | According to SAFe, which of the following types of work should fit into one Iteration for one team?
| Stories | X | X
Features
Epics
Tasks
20 | What is one practice Scrum Masters/Team Coaches can use to run successful meetings?
Maintain vague agendas to allow for any urgent issues
Allow individuals to override timeboxes to ensure full discussions
| Leave meetings with clear action items | X | X
Schedule meetings around the Product Owner to ensure they are able to make final decisions
21 | What is one benefit of having an IP Iteration every PI?
| It creates a timeboxed opportunity for team growth |  | X
It creates a guardrail for teams working too hard
It creates a chance for teams to manage quality
| It creates an estimating buffer for meeting PI objectives | X
22 | What is the first step of the problem-solving workshop?
Perform a root-cause analysis
| Agree on the problem to solve | X | X
Identify the biggest root cause
Restate the new problem for the biggest root cause
23 | What is one method a Scrum Master/Team Coach can use to help teams overcome a fear of conflict?
Giving every team member the opportunity to contribute
| Aligning to shared commitments | X | X
Scheduling regular Team Syncs
Enforcing work-in-process limits
24 | According to SAFe, what is one output of a successful Iteration Retrospective?
Updated dependencies between Stories
| Improvement Stories | X | X
Iteration Goals
Updated ART metrics
25 | What is one potential root cause of Team Sync anti-patterns?
| Lack of collective ownership | X | X
Frequent verification and integration during the Iteration
Occasional conflict within the team
Overcommunication between team members
26 | What is one example of Scrum Masters/Team Coaches helping without diminishing the commitment of others?
Coaching the team to refrain from relying on external resources
Encouraging handoffs so each team member contributes to the work
| Facilitating necessary meetings for the team | X | X
Demoing the team's completed work
27 | According to SAFe, what is one Iteration Retrospective anti-pattern?
The team only shares issues that are too big to be solved
| The team only brings up issues that are outside of their control to address | X | X
The team only shares issues that are too small to result in real improvement
The team only shares issues that cannot be measured
28 | What is one recommended practice for Scrum Masters/Team Coaches when coaching teams on presenting a draft plan at PI Planning?
| Ensure the team has Stories written for the first two Iterations of the increment | X
Secure support from other teams on how work will be shared and completed
| Identify as many risks and dependencies as possible for the management review |  | X
Align on how the team will answer questions about their proposed objectives
29 | How does the "C" in the CALMR approach to DevOps help teams manage tensions caused by differing needs?
By committing to a balance of speed and quality
By identifying a collaborative approach to deployment
By establishing communication between different teams
| By creating a culture of shared responsibility | X | X
30 | What is a team's primary goal in an Iteration?
Maintaining steady team syncs across the Iteration
Managing scope at the start of the Iteration
| Delivering working functionality at the end of the Iteration | X | X
Sharing progress with the organization during the Iteration
31 | What is one way a servant leader can support team members in decision-making?
| Give each team member the opportunity to contribute | X | X
Identify solutions to problems the team surfaces
Perform regular retrospectives on behalf of the team
Support teams in affinity mapping their concerns
32 | What is one element of the CALMR approach to DevOps?
Maximize work in process
Relentlessly reduce risk
| Lean flow accelerates delivery | X | X
Activate the knowledge worker
33 | What is one recommended practice for Scrum Masters/Team Coaches when facilitating Iteration Review?
| Begin to consider how and what to demo in Iteration Planning | X | X
Encourage team members to spend 3+ hours preparing
Limit participants to just the team members
Encourage the team member with the best presentation skills to demo each Iteration
34 | During which of the following stages of team development do team members stop focusing on their own goals and begin focusing on developing better ways of working together?
| Norming | X | X
Forming
Storming
Transforming
35 | What is one anti-pattern that emerges when teams do not spend enough time refining the backlog?
Teams arrive to Iteration Planning without specified goals
Teams enter retrospectives without improvement ideas
Teams arrive to Team Sync without progress to share
| Teams enter new Iterations without enough Stories prepared | X | X
36 | What is one practice Scrum Masters/Team Coaches can use to facilitate conflict management?
Implement a formal complaints system
Escalate conflicts to the Release Train Engineer
| Enforce working agreements | X | X
Encourage team members to resolve conflicts on their own
37 | What is one purpose of Iteration Goals?
To identify what to present in System Demo
| To align team members to common objectives | X | X
To get feedback from the organization
To communicate which Stories will be completed during the Iteration
38 | Team A works collaboratively on new functionality for a customer application. The acceptance criteria have each been minimally met. Team A decides to release the functionality with a method for collecting direct customer feedback. Which of the following high-performing team characteristics is Team A demonstrating?
Focusing on success over trying to avoid failures
Taking appropriate risks without fear of failure
| Using regular feedback loops built into the learning cycle | X | X
Balancing abilities on the team with the challenge of the work
39 | During which of the following Agile Team events do team members estimate relative story sizes?
| Iteration Planning |  | X
| Backlog Refinement | X
Iteration Review
Iteration Retrospective
40 | What can a Scrum Master/Team Coach recommend to a team that is showing signs of burnout, not addressing increasing technical debt, and acting out of urgency rather than considering innovation?
| A constructive IP Iteration at the end of each PI | X | X
A communicative retrospective at the end of each Iteration
A careful plan at the beginning of each Iteration
A collective Iteration Review and demo each Iteration
41 | What is one benefit of holding regular system demos?
Problems can be escalated to ART leadership
| Execution can be measured across the whole ART |  | X
Bottlenecks can be identified early by the teams
| Deliverables are reviewed with stakeholders | X
42 | Who are important attendees to the PI System Demo?
| Feature Owners | X
| Portfolio Management | X
| Business Owners | X | X
Board Members
43 | Team A has decided to use the IP Iteration to continue the finalizing Feature delivery work they have been working on for the past two Iterations. What is one effect Team A might experience by continuing to stay heads-down rather than using the IP Iteration as intended?
Individual team members could lose an opportunity to consider their team work more holistically
Individual team members could lose an opportunity to keep their technical skills current
| Individual team members could lose an opportunity to refresh their motivation | X | X
Individual team members could lose an opportunity to learn from one another
44 | What is one way uncommitted objectives help Agile Teams make a plan for the PI?
They create an opportunity for teams to take on harder work
| They maintain the predictability of achieving the objectives | X | X
They ensure the team has additional development options
They generate additional ways to measure team progress
45 | What is one anti-pattern of the Inspect and Adapt?
Not enough team members attend the PI System demo
| No actionable improvement Features are created | X | X
Too many ideas enter the problem-solving workshop
Only one problem is identified by each team in the retrospective